## 封面
天堂2盟约 · 公会助手
研发进度办公报表
字段 | 内容
报告日期 | 2026-09-02
统计区间 | 2026-08-11 至 2026-09-02
数据来源 | GitHub Pull Requests（bigdaddyLIU）
PR 总数 | 44
已合并到 main | 0
当前状态 | 全部 44 个 PR 仍为 Open，且多为串联叠加分支
说明 | 本表用于周会/复盘。main 仍只有 README，功能代码在功能分支链上。

## PR明细
编号 | 标题 | 模块 | 类型 | 状态 | 草稿 | 创建日期 | 更新时间 | 周次 | 源分支 | 目标分支 | 链接
1 | 公会助手：身份登录、功能首页与管理后台 | 登录 / 基础平台 | 功能开发 | 草稿 | 是 | 2026-08-11 | 2026-08-11 21:05 | 2026-08-10 ~ 2026-08-16 | cursor/guild-login-system-419b | main | https://github.com/larryliuxing/bigdaddyLIU/pull/1
2 | fix: HTTP 登录 Cookie 丢失导致无法进入首页 | 登录 / 基础平台 | 缺陷修复 | 草稿 | 是 | 2026-08-12 | 2026-08-12 04:04 | 2026-08-10 ~ 2026-08-16 | cursor/fix-login-redirect-419b | main | https://github.com/larryliuxing/bigdaddyLIU/pull/2
3 | fix: 增强战力截图角色名 OCR 识别 | 排行榜 / OCR | 缺陷修复 | 草稿 | 是 | 2026-08-12 | 2026-08-12 16:44 | 2026-08-10 ~ 2026-08-16 | cursor/fix-leaderboard-ocr-name-419b | cursor/fix-login-redirect-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/3
4 | 限制账户与拍卖物品管理仅限管理员后台 | 成员 / 权限 | 功能开发 | 草稿 | 是 | 2026-08-12 | 2026-08-12 17:03 | 2026-08-10 ~ 2026-08-16 | cursor/admin-only-permissions-419b | cursor/fix-leaderboard-ocr-name-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/4
5 | 修复拍卖场次时间弹回并统一北京时间 | 拍卖竞价 | 缺陷修复 | 草稿 | 是 | 2026-08-12 | 2026-08-12 17:20 | 2026-08-10 ~ 2026-08-16 | cursor/fix-auction-beijing-time-419b | cursor/admin-only-permissions-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/5
6 | 重构拍卖后台：场次列表与拍品管理流程 | 拍卖竞价 | 功能开发 | 草稿 | 是 | 2026-08-12 | 2026-08-12 17:36 | 2026-08-10 ~ 2026-08-16 | cursor/auction-session-workflow-419b | cursor/fix-auction-beijing-time-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/6
7 | 拍品图仅识别顶部装备名称 | 拍卖竞价 | 功能开发 | 草稿 | 是 | 2026-08-12 | 2026-08-12 17:56 | 2026-08-10 ~ 2026-08-16 | cursor/auction-item-name-ocr-419b | cursor/auction-session-workflow-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/7
8 | 拍卖改为全部拍品同时竞拍 | 拍卖竞价 | 功能开发 | 草稿 | 是 | 2026-08-12 | 2026-08-12 18:01 | 2026-08-10 ~ 2026-08-16 | cursor/auction-simultaneous-items-419b | cursor/auction-item-name-ocr-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/8
9 | 拍卖分红：可调税率、按拍品明细与公示总表 | 拍卖竞价 | 功能开发 | 草稿 | 是 | 2026-08-12 | 2026-08-12 18:42 | 2026-08-10 ~ 2026-08-16 | cursor/auction-dividend-tax-breakdown-419b | cursor/auction-simultaneous-items-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/9
10 | fix: improve auction item name OCR accuracy | 拍卖竞价 | 缺陷修复 | 草稿 | 是 | 2026-08-12 | 2026-08-12 18:57 | 2026-08-10 ~ 2026-08-16 | cursor/auction-item-ocr-accuracy-419b | cursor/auction-dividend-tax-breakdown-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/10
11 | feat: show high/low/avg prices when adding auction items | 拍卖竞价 | 功能开发 | 草稿 | 是 | 2026-08-12 | 2026-08-12 18:58 | 2026-08-10 ~ 2026-08-16 | cursor/auction-add-form-price-stats-419b | cursor/auction-item-ocr-accuracy-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/11
12 | feat: BOSS settings labels, drop images, and admin timers | BOSS 计时 | 功能开发 | 草稿 | 是 | 2026-08-12 | 2026-08-12 19:44 | 2026-08-10 ~ 2026-08-16 | cursor/boss-settings-drops-timer-419b | cursor/auction-add-form-price-stats-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/12
13 | feat: auction high-bid fanfare music and danmaku | 拍卖竞价 | 功能开发 | 草稿 | 是 | 2026-08-12 | 2026-08-12 21:26 | 2026-08-10 ~ 2026-08-16 | cursor/auction-bid-fanfare-419b | cursor/boss-settings-drops-timer-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/13
14 | feat: add 天堂2盟约 brand title on home | 首页 / 品牌 | 功能开发 | 草稿 | 是 | 2026-08-12 | 2026-08-12 21:44 | 2026-08-10 ~ 2026-08-16 | cursor/home-brand-title-419b | cursor/auction-bid-fanfare-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/14
15 | fix: 成员清退 + 清空成员/拍卖（留 admin 与 BOSS） | 成员 / 权限 | 缺陷修复 | 草稿 | 是 | 2026-08-12 | 2026-08-12 21:58 | 2026-08-10 ~ 2026-08-16 | cursor/fix-admin-delete-member-419b | cursor/home-brand-title-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/15
16 | perf: BOSS 设置页列表加载加速 | BOSS 计时 | 性能优化 | 草稿 | 是 | 2026-08-13 | 2026-08-13 13:33 | 2026-08-10 ~ 2026-08-16 | cursor/fix-boss-settings-load-419b | cursor/fix-admin-delete-member-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/16
17 | fix: BOSS 计时规则（下次刷新 vs 击杀） | BOSS 计时 | 缺陷修复 | 草稿 | 是 | 2026-08-13 | 2026-08-13 14:03 | 2026-08-10 ~ 2026-08-16 | cursor/fix-boss-timer-rules-419b | cursor/fix-boss-settings-load-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/17
18 | feat: BOSS 倒计时排序、加大名称、投票人数设置 | BOSS 计时 | 功能开发 | 草稿 | 是 | 2026-08-13 | 2026-08-13 14:33 | 2026-08-10 ~ 2026-08-16 | cursor/boss-countdown-sort-vote-need-419b | cursor/fix-boss-timer-rules-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/18
19 | chore: 正式上线清理（删测试、清拍卖、改管理员密码） | 上线 / 运维 | 运维清理 | 草稿 | 是 | 2026-08-17 | 2026-08-17 07:50 | 2026-08-17 ~ 2026-08-23 | cursor/prod-golive-cleanup-419b | cursor/boss-countdown-sort-vote-need-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/19
20 | fix: 排行榜战力只识别左上角（取消双校验） | 排行榜 / OCR | 缺陷修复 | 草稿 | 是 | 2026-08-21 | 2026-08-22 01:04 | 2026-08-17 ~ 2026-08-23 | cursor/perf-leaderboard-ocr-419b | cursor/prod-golive-cleanup-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/20
21 | fix: 识别角色下方「战斗力」后的数字（更快更准） | 排行榜 / OCR | 缺陷修复 | 草稿 | 是 | 2026-08-22 | 2026-08-22 01:32 | 2026-08-17 ~ 2026-08-23 | cursor/fix-power-ocr-topleft-419b | cursor/perf-leaderboard-ocr-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/21
22 | feat: 左上战力改用服务端 PP-OCR（准确+速度） | 排行榜 / OCR | 功能开发 | 草稿 | 是 | 2026-08-22 | 2026-08-22 01:42 | 2026-08-17 ~ 2026-08-23 | cursor/paddleocr-power-419b | cursor/fix-power-ocr-topleft-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/22
23 | feat: 点选战力数字 + 点选名字识别（4–6 位） | 排行榜 / OCR | 功能开发 | 草稿 | 是 | 2026-08-22 | 2026-08-22 01:53 | 2026-08-17 ~ 2026-08-23 | cursor/click-power-name-ocr-419b | cursor/paddleocr-power-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/23
24 | feat: 拍卖税率改为按场次设置（0%–10%） | 拍卖竞价 | 功能开发 | 待审 | 否 | 2026-08-26 | 2026-08-26 19:17 | 2026-08-24 ~ 2026-08-30 | cursor/auction-session-tax-419b | cursor/click-power-name-ocr-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/24
25 | 预约未开拍时先展示拍品，到点才能出价 | 拍卖竞价 | 功能开发 | 待审 | 否 | 2026-08-26 | 2026-08-26 19:44 | 2026-08-24 ~ 2026-08-30 | cursor/auction-preview-waiting-419b | cursor/auction-session-tax-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/25
26 | 紫/粉拍品最后一分钟出价加时 | 拍卖竞价 | 功能开发 | 待审 | 否 | 2026-08-26 | 2026-08-26 19:57 | 2026-08-24 ~ 2026-08-30 | cursor/auction-quality-extend-419b | cursor/auction-preview-waiting-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/26
27 | 后台可配置排行榜合格战力百分比 | 排行榜 / OCR | 功能开发 | 待审 | 否 | 2026-08-26 | 2026-08-26 20:18 | 2026-08-24 ~ 2026-08-30 | cursor/leaderboard-threshold-419b | cursor/auction-quality-extend-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/27
28 | 加大排行榜点名识别范围 | 排行榜 / OCR | 功能开发 | 待审 | 否 | 2026-08-26 | 2026-08-26 23:42 | 2026-08-24 ~ 2026-08-30 | cursor/leaderboard-name-ocr-range-419b | cursor/leaderboard-threshold-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/28
29 | 首页更新日志、拍卖动态可滚动、结束后结果上移 | 首页 / 品牌 | 功能开发 | 待审 | 否 | 2026-08-27 | 2026-08-27 00:46 | 2026-08-24 ~ 2026-08-30 | cursor/home-changelog-auction-feed-419b | cursor/leaderboard-name-ocr-range-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/29
30 | 点名识别框收回并加快，避免又大又卡 | 排行榜 / OCR | 性能优化 | 待审 | 否 | 2026-08-27 | 2026-08-27 01:01 | 2026-08-24 ~ 2026-08-30 | cursor/name-ocr-trim-speed-419b | cursor/home-changelog-auction-feed-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/30
31 | 首页更新日志挪到排行榜下面 | 首页 / 品牌 | 功能开发 | 待审 | 否 | 2026-08-27 | 2026-08-27 20:45 | 2026-08-24 ~ 2026-08-30 | cursor/changelog-below-leaderboard-419b | cursor/name-ocr-trim-speed-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/31
32 | 点名识别支持洛丶洛，去掉左右图标干扰 | 排行榜 / OCR | 功能开发 | 待审 | 否 | 2026-08-28 | 2026-08-28 00:09 | 2026-08-24 ~ 2026-08-30 | cursor/name-ocr-dot-419b | cursor/changelog-below-leaderboard-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/32
33 | 名字识别框为战力框两倍，并加强浅蓝识别 | 排行榜 / OCR | 功能开发 | 待审 | 否 | 2026-08-28 | 2026-08-28 16:14 | 2026-08-24 ~ 2026-08-30 | cursor/name-ocr-blue-range-419b | cursor/name-ocr-dot-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/33
34 | fix: 识别飞飞、抖音绵羊这类饱和青色角色名 | 排行榜 / OCR | 缺陷修复 | 待审 | 否 | 2026-08-28 | 2026-08-28 16:38 | 2026-08-24 ~ 2026-08-30 | cursor/name-ocr-cyan-hud-419b | cursor/name-ocr-blue-range-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/34
35 | feat: 后台可移除已上榜成员的错误战力记录 | 排行榜 / OCR | 功能开发 | 待审 | 否 | 2026-08-28 | 2026-08-28 16:42 | 2026-08-24 ~ 2026-08-30 | cursor/admin-remove-leaderboard-419b | cursor/name-ocr-cyan-hud-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/35
36 | feat: 盟员点 BOSS 立刻重开倒计时，并显示上次标记的人 | BOSS 计时 | 功能开发 | 草稿 | 是 | 2026-08-31 | 2026-08-31 10:41 | 2026-08-31 ~ 2026-09-06 | cursor/boss-click-timer-419b | cursor/auction-session-tax-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/36
37 | feat: 后台截图识别批量调整 BOSS 计时 | BOSS 计时 | 功能开发 | 草稿 | 是 | 2026-08-31 | 2026-08-31 11:26 | 2026-08-31 ~ 2026-09-06 | cursor/boss-timer-ocr-419b | cursor/boss-click-timer-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/37
38 | feat: 粉色拍品限价竞价后匿名投票，平票掷点结算 | 拍卖竞价 | 功能开发 | 草稿 | 是 | 2026-09-01 | 2026-09-01 19:40 | 2026-08-31 ~ 2026-09-06 | cursor/pink-auction-vote-419b | cursor/boss-timer-ocr-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/38
39 | fix: 恢复首页更新公告，避免后续改动再冲掉 | 首页 / 品牌 | 缺陷修复 | 草稿 | 是 | 2026-09-01 | 2026-09-01 19:50 | 2026-08-31 ~ 2026-09-06 | cursor/restore-home-changelog-419b | cursor/pink-auction-vote-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/39
40 | feat: 拍卖颜色拆成紫色、普通粉色、特殊粉色 | 拍卖竞价 | 功能开发 | 草稿 | 是 | 2026-09-01 | 2026-09-01 20:31 | 2026-08-31 ~ 2026-09-06 | cursor/pink-ordinary-special-419b | cursor/restore-home-changelog-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/40
41 | perf: speed up auction, dividends, and admin listing loads | 拍卖竞价 | 性能优化 | 草稿 | 是 | 2026-09-02 | 2026-09-02 16:29 | 2026-08-31 ~ 2026-09-06 | cursor/auction-load-speed-419b | cursor/pink-ordinary-special-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/41
42 | feat: restore admin leaderboard pass-line percent | 排行榜 / OCR | 功能开发 | 草稿 | 是 | 2026-09-02 | 2026-09-02 16:33 | 2026-08-31 ~ 2026-09-06 | cursor/restore-leaderboard-threshold-419b | cursor/auction-load-speed-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/42
43 | feat: restore admin removal of incorrect leaderboard records | 排行榜 / OCR | 功能开发 | 草稿 | 是 | 2026-09-02 | 2026-09-02 16:34 | 2026-08-31 ~ 2026-09-06 | cursor/restore-leaderboard-remove-419b | cursor/restore-leaderboard-threshold-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/43
44 | fix: restore cyan HUD name OCR for 飞飞 and 抖音绵羊 | 排行榜 / OCR | 缺陷修复 | 草稿 | 是 | 2026-09-02 | 2026-09-02 22:08 | 2026-08-31 ~ 2026-09-06 | cursor/restore-name-ocr-cyan-419b | cursor/restore-leaderboard-remove-419b | https://github.com/larryliuxing/bigdaddyLIU/pull/44

## 模块汇总
模块 | PR数量 | 占比
排行榜 / OCR | 15 | 0.341
拍卖竞价 | 14 | 0.318
BOSS 计时 | 6 | 0.136
首页 / 品牌 | 4 | 0.091
登录 / 基础平台 | 2 | 0.045
成员 / 权限 | 2 | 0.045
上线 / 运维 | 1 | 0.023

## 周度产出
周次 | PR数量
2026-08-10 ~ 2026-08-16 | 18
2026-08-17 ~ 2026-08-23 | 5
2026-08-24 ~ 2026-08-30 | 12
2026-08-31 ~ 2026-09-06 | 9

## 类型与状态
分类 | 项目 | 数量
类型 | 功能开发 | 29
类型 | 缺陷修复 | 11
类型 | 性能优化 | 3
类型 | 运维清理 | 1
状态 | 草稿 | 32
状态 | 待审 | 12

## 分支链路
风险说明
编号 | 源分支 | 目标分支 | 标题
1 | cursor/guild-login-system-419b | main | 公会助手：身份登录、功能首页与管理后台
2 | cursor/fix-login-redirect-419b | main | fix: HTTP 登录 Cookie 丢失导致无法进入首页
3 | cursor/fix-leaderboard-ocr-name-419b | cursor/fix-login-redirect-419b | fix: 增强战力截图角色名 OCR 识别
4 | cursor/admin-only-permissions-419b | cursor/fix-leaderboard-ocr-name-419b | 限制账户与拍卖物品管理仅限管理员后台
5 | cursor/fix-auction-beijing-time-419b | cursor/admin-only-permissions-419b | 修复拍卖场次时间弹回并统一北京时间
6 | cursor/auction-session-workflow-419b | cursor/fix-auction-beijing-time-419b | 重构拍卖后台：场次列表与拍品管理流程
7 | cursor/auction-item-name-ocr-419b | cursor/auction-session-workflow-419b | 拍品图仅识别顶部装备名称
8 | cursor/auction-simultaneous-items-419b | cursor/auction-item-name-ocr-419b | 拍卖改为全部拍品同时竞拍
9 | cursor/auction-dividend-tax-breakdown-419b | cursor/auction-simultaneous-items-419b | 拍卖分红：可调税率、按拍品明细与公示总表
10 | cursor/auction-item-ocr-accuracy-419b | cursor/auction-dividend-tax-breakdown-419b | fix: improve auction item name OCR accuracy
11 | cursor/auction-add-form-price-stats-419b | cursor/auction-item-ocr-accuracy-419b | feat: show high/low/avg prices when adding auction items
12 | cursor/boss-settings-drops-timer-419b | cursor/auction-add-form-price-stats-419b | feat: BOSS settings labels, drop images, and admin timers
13 | cursor/auction-bid-fanfare-419b | cursor/boss-settings-drops-timer-419b | feat: auction high-bid fanfare music and danmaku
14 | cursor/home-brand-title-419b | cursor/auction-bid-fanfare-419b | feat: add 天堂2盟约 brand title on home
15 | cursor/fix-admin-delete-member-419b | cursor/home-brand-title-419b | fix: 成员清退 + 清空成员/拍卖（留 admin 与 BOSS）
16 | cursor/fix-boss-settings-load-419b | cursor/fix-admin-delete-member-419b | perf: BOSS 设置页列表加载加速
17 | cursor/fix-boss-timer-rules-419b | cursor/fix-boss-settings-load-419b | fix: BOSS 计时规则（下次刷新 vs 击杀）
18 | cursor/boss-countdown-sort-vote-need-419b | cursor/fix-boss-timer-rules-419b | feat: BOSS 倒计时排序、加大名称、投票人数设置
19 | cursor/prod-golive-cleanup-419b | cursor/boss-countdown-sort-vote-need-419b | chore: 正式上线清理（删测试、清拍卖、改管理员密码）
20 | cursor/perf-leaderboard-ocr-419b | cursor/prod-golive-cleanup-419b | fix: 排行榜战力只识别左上角（取消双校验）
21 | cursor/fix-power-ocr-topleft-419b | cursor/perf-leaderboard-ocr-419b | fix: 识别角色下方「战斗力」后的数字（更快更准）
22 | cursor/paddleocr-power-419b | cursor/fix-power-ocr-topleft-419b | feat: 左上战力改用服务端 PP-OCR（准确+速度）
23 | cursor/click-power-name-ocr-419b | cursor/paddleocr-power-419b | feat: 点选战力数字 + 点选名字识别（4–6 位）
24 | cursor/auction-session-tax-419b | cursor/click-power-name-ocr-419b | feat: 拍卖税率改为按场次设置（0%–10%）
25 | cursor/auction-preview-waiting-419b | cursor/auction-session-tax-419b | 预约未开拍时先展示拍品，到点才能出价
26 | cursor/auction-quality-extend-419b | cursor/auction-preview-waiting-419b | 紫/粉拍品最后一分钟出价加时
27 | cursor/leaderboard-threshold-419b | cursor/auction-quality-extend-419b | 后台可配置排行榜合格战力百分比
28 | cursor/leaderboard-name-ocr-range-419b | cursor/leaderboard-threshold-419b | 加大排行榜点名识别范围
29 | cursor/home-changelog-auction-feed-419b | cursor/leaderboard-name-ocr-range-419b | 首页更新日志、拍卖动态可滚动、结束后结果上移
30 | cursor/name-ocr-trim-speed-419b | cursor/home-changelog-auction-feed-419b | 点名识别框收回并加快，避免又大又卡
31 | cursor/changelog-below-leaderboard-419b | cursor/name-ocr-trim-speed-419b | 首页更新日志挪到排行榜下面
32 | cursor/name-ocr-dot-419b | cursor/changelog-below-leaderboard-419b | 点名识别支持洛丶洛，去掉左右图标干扰
33 | cursor/name-ocr-blue-range-419b | cursor/name-ocr-dot-419b | 名字识别框为战力框两倍，并加强浅蓝识别
34 | cursor/name-ocr-cyan-hud-419b | cursor/name-ocr-blue-range-419b | fix: 识别飞飞、抖音绵羊这类饱和青色角色名
35 | cursor/admin-remove-leaderboard-419b | cursor/name-ocr-cyan-hud-419b | feat: 后台可移除已上榜成员的错误战力记录
36 | cursor/boss-click-timer-419b | cursor/auction-session-tax-419b | feat: 盟员点 BOSS 立刻重开倒计时，并显示上次标记的人
37 | cursor/boss-timer-ocr-419b | cursor/boss-click-timer-419b | feat: 后台截图识别批量调整 BOSS 计时
38 | cursor/pink-auction-vote-419b | cursor/boss-timer-ocr-419b | feat: 粉色拍品限价竞价后匿名投票，平票掷点结算
39 | cursor/restore-home-changelog-419b | cursor/pink-auction-vote-419b | fix: 恢复首页更新公告，避免后续改动再冲掉
40 | cursor/pink-ordinary-special-419b | cursor/restore-home-changelog-419b | feat: 拍卖颜色拆成紫色、普通粉色、特殊粉色
41 | cursor/auction-load-speed-419b | cursor/pink-ordinary-special-419b | perf: speed up auction, dividends, and admin listing loads
42 | cursor/restore-leaderboard-threshold-419b | cursor/auction-load-speed-419b | feat: restore admin leaderboard pass-line percent
43 | cursor/restore-leaderboard-remove-419b | cursor/restore-leaderboard-threshold-419b | feat: restore admin removal of incorrect leaderboard records
44 | cursor/restore-name-ocr-cyan-419b | cursor/restore-leaderboard-remove-419b | fix: restore cyan HUD name OCR for 飞飞 and 抖音绵羊